## Project_Planner
Fettuccine Project Planner
|  |  |  | Michaela | [5 empty] | Nayam |  |  |  |  | Dan |  |  |  |  | Dionysis | [7 empty] | Teamwork
ACTIVITY | 08-14 Jan 2018 | [6 empty] | 15-21 Jan 2018 | [6 empty] | 22-28 Jan 2018 | [6 empty] | 29 Jan - 04 Feb 2018 | [6 empty] | 05-11 Feb 2018 | [6 empty] | 12-16 Feb 2018
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Basic GUI - HTML Basics - Flask - MySQL | bar: 08-14 Jan 2018 M to 15-21 Jan 2018 S
Family Table | bar: 08-14 Jan 2018 M to 22-28 Jan 2018 F
Create MySQL database - Website's Basics | bar: 08-14 Jan 2018 T to 15-21 Jan 2018 T
Grab the data and format it from Table Br. | bar: 08-14 Jan 2018 T to 15-21 Jan 2018 T
Search Bar - check boxes - visualising data - Website's Basics | bar: 08-14 Jan 2018 T to 22-28 Jan 2018 W
Distribution of retrotransposons
Visualise the whole genome | bar: 15-21 Jan 2018 W to 22-28 Jan 2018 T
Map LINE1 & HRV | bar: 15-21 Jan 2018 W to 22-28 Jan 2018 T
Extra: Translated products?
Translated Products
Find them | bar: 15-21 Jan 2018 S to 22-28 Jan 2018 F
Translated products into database | bar: 22-28 Jan 2018 S to 22-28 Jan 2018 S
Translated Products relationships
Relationships based on alignment scores between AAs | bar: 22-28 Jan 2018 S to 29 Jan - 04 Feb 2018 S
Visualise the distances | bar: 22-28 Jan 2018 F to 05-11 Feb 2018 M
Create an interactive environment (drag&drop) | bar: 22-28 Jan 2018 F to 29 Jan - 04 Feb 2018 S
Protein-protein interactions? | bar: 29 Jan - 04 Feb 2018 W to 05-11 Feb 2018 W
Pep-seq to Retrotransposon family
Handle of the input (Either sequence(s) or fasta file) | bar: 15-21 Jan 2018 W to 15-21 Jan 2018 F
Mzid-Mztab Handling | bar: 15-21 Jan 2018 F to 15-21 Jan 2018 S
Code that determines if there is a corresponding RT family | bar: 22-28 Jan 2018 M to 22-28 Jan 2018 T
Return the resulting family | bar: 22-28 Jan 2018 W to 22-28 Jan 2018 F
Store the results - Expression Atlas | bar: 22-28 Jan 2018 S to 29 Jan - 04 Feb 2018 T; 05-11 Feb 2018 S to 12-16 Feb 2018 M
Documentation - About us | bar: 05-11 Feb 2018 M to 12-16 Feb 2018 W
GUI – Debugging | bar: 29 Jan - 04 Feb 2018 M to 05-11 Feb 2018 S
Optimisation | bar: 05-11 Feb 2018 M to 12-16 Feb 2018 W