## Project_Planner
Project Planner
|  |  |  | Michaela | [5 empty] | Nayam |  |  |  |  | Dan |  |  |  |  | Dionysis | [7 empty] | Teamwork
ACTIVITY | 08-14 Jan 2018 | [6 empty] | 15-21 Jan 2018 | [6 empty] | 22-28 Jan 2018 | [6 empty] | 29 Jan - 04 Feb 2018 | [6 empty] | 05-11 Feb 2018 | [6 empty] | 12-16 Feb 2018
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Basic GUI - HTML Basics | bar: 08-14 Jan 2018 M to 08-14 Jan 2018 W; 15-21 Jan 2018 M to 22-28 Jan 2018 F
Family Table | bar: 08-14 Jan 2018 M to 22-28 Jan 2018 F
Create MySQL database
Use API to grab the data and format it from Table Br. | bar: 08-14 Jan 2018 T to 15-21 Jan 2018 T
Find the transcript data
Create Search bar - table Visualise the database information | bar: 08-14 Jan 2018 T to 15-21 Jan 2018 T
Distribution of retrotransposons | bar: 15-21 Jan 2018 W to 22-28 Jan 2018 M
Visualise the whole genome | bar: 15-21 Jan 2018 W to 22-28 Jan 2018 M
Map LINE1 & HRV | bar: 15-21 Jan 2018 W to 22-28 Jan 2018 M
Transcripts | bar: 15-21 Jan 2018 W to 22-28 Jan 2018 M
Extra: Translated products?
Translated Products
Find them
Translated products into database
Extra: Predicted/Actual
Visualise the database information
GUI
Translated Products relationships
Relationships based on alignment scores between AAs
Visualise the distances
Create an interactive environment (drag&drop)
Protein-protein interactions?
Pep-seq to Retrotransposon family
Handle of the input (Either sequence(s) or fasta file)
Blastp against the AAs of the Database
Code that determines if there is a corresponding RT family
Return the resulting family (or nothing) and blast results
RT in sample?
Handle uploaded file
Use the previous code
Store the results - Expression Atlas
Documentation - About us